## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint - 1
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Initial Selection | 5 | Aman Akash
Task_1 | Screen should display the option for Admin/Vendor login / Registration and Customer login / Registration |  | Aman Akash |  | 7 | 5 | 3 | 0 | 0 | 0
User Story #2 | User Registration | 8 | Aman Akash
Task_1 | When the User clicks on Admin Registration link, it should re-direct to registration form |  | Aman Akash |  | 3 | 1 | 1 | 5 | 0 | 1
Task_2 | Admin needs to fill some of the basic attributes/fields as mentioned below in the requirement: First Name, Last Name, Contact Number, Email, Password |  | Aman Akash |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_3 | Before entering the next field, each field should be validated and appropriate error message should be displayed near the corresponding text box. |  | Aman Akash |  | 3 | 1 | 5 | 0 | 1 | 0
Task_4 | User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red |  | Aman Akash |  | 0.5 | 1 | 2 | 3 | 1 | 0
Task_5 | Post-successful field level validation, save the information in the database |  | Aman Akash |  | 3 | 1 | 0 | 5 | 1 | 0
Task_6 | Upon saving the information in the database, display the message ‘Your details are submitted successfully’ |  | Aman Akash |  | 3 | 1 | 1 | 5 | 1 | 0
Task_7 | Admin should be able to view the New vendor registration |  | Aman Akash |  | 2 | 2 | 5 | 0 | 1 | 0
Task_8 | Admin should approve / reject the vendor Request. |  | Aman Akash |  | 5 | 5 | 9 | 5 | 1 | 0
Task_9 | If rejected, the Vendor should not be allowed to login with the registered credentials |  | Aman Akash |  | 8 | 8 | 8 | 8 | 8 | 8
Task_10 | Vendor should be notified upon approval/rejection while trying to enter the application. |  | Aman Akash |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
User Story #3 | User Authentication | 5 | Phani Mahesh Jonnalagadda
Task_1 | A registered User – is able click ‘Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. |  | Phani Mahesh Jonnalagadda |  | 5 | 3 | 1 | 0.5 | 3 | 0
User Story #4 | Admin Registration | 5 | Phani Mahesh Jonnalagadda
Task_1 | Admin should select the Admin option |  | Phani Mahesh Jonnalagadda |  | 3 | 5 | 2 | 3 | 1 | 0
Task_2 | Admin's User id and password should be pre-loaded in the database, which can be used to log in. |  | Phani Mahesh Jonnalagadda |  | 2 | 2 | 5 | 0 | 1 | 0
User Story #5 | Admin Authentication | 5 | Aman Akash
Task_1 | A registered Admin – is able click ‘Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. |  | Aman Akash |  | 3 | 2 | 3 | 1 | 0 | 5
User Story #6 | Admin Approval | 5 | Phani Mahesh Jonnalagadda
Task_1 | Any vendor registration should be approved by Admin |  | Phani Mahesh Jonnalagadda |  | 5 | 5 | 3 | 2 | 5 | 3
Task_2 | Only on approval, vendor should be able to login |  | Phani Mahesh Jonnalagadda |  | 3 | 3 | 3 | 3 | 3 | 0
Task_3 | Error message such as approval pending should be displayed, when such vendor tries to login" |  | Phani Mahesh Jonnalagadda |  | 2 | 1 | 0 | 3 | 5 | 3
User Story #7 | Vendor Details | 5 | Vishal Choudary
Task_1 | Vendor should be able to fill in his details like address/ phone number, email and other contact information |  | Vishal Choudary |  | 6 | 2 | 8 | 8 | 0.5 | 0
Task_2 | Only on approval, vendor should be able to login |  | Vishal Choudary |  | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0
Task_3 | Error message such as approval pending should be displayed, when such vendor tries to login" |  | Vishal Choudary |  | 5 | 5 | 9 | 5 | 1 | 0
User Story #8 | Service Center Details | 8 | Vishal Choudary
Task_1 | Vendor should click on the add service tab to select the service he provides |  | Vishal Choudary |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Task_2 | All category divisions available should be listed for the Service and Vendor should be able to select one |  | Vishal Choudary |  | 3 | 2 | 3 | 5 | 1 | 0
Task_3 | Vendor providing service should provide the contact details, available time and Maps option to locate |  | Vishal Choudary |  | 5 | 3 | 3 | 8 | 5 | 3
Task_4 | Vendor should have a field to update his service details |  | Vishal Choudary |  | 3 | 3 | 5 | 3 | 1 | 0
Task_5 | Vendor failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red |  | Vishal Choudary |  | 2 | 2 | 3 | 5 | 8 | 0
Task_6 | Upon saving the information in the database, display the message ‘Your details are submitted successfully’. |  | Vishal Choudary |  | 3 | 8 | 8 | 8 | 8 | 8
Task_7 | The service details entered should be linked with the vendor ID creating it |  | Vishal Choudary |  | 5 | 9 | 3 | 4 | 1 | 0
Task_8 | Vendor should have the option to edit / delete the Service details entered by them. |  | Vishal Choudary |  | 3 | 3 | 2 | 5 | 1 | 0
User Story #9 | Search Service Center | 5
Task_1 | All Users should be able to search for service center |  | Vishal Choudary |  | 3 | 2 | 4 | 9 | 4 | 0
Task_2 | Search can be based on the service type, location,name of the service center. |  | Himmat Singh |  | 1 | 3 | 0.5 | 8 | 3 | 1
Task_3 | Search result should display the service center details |  | Himmat Singh |  | 6 | 5 | 3 | 3 | 2 | 0
Task_4 | clicking the service center displayed, it should open the service center details page |  | Himmat Singh |  | 5 | 8 | 5 | 2 | 1 | 0
Task_5 | From which Customer should be able book for service |  | Vishal Choudary |  | 3 | 2 | 8 | 3 | 5 | 1
Task_6 | Vendor should be edit/delete the details |  | Aman Akash |  | 5 | 0.5 | 2 | 3 | 5 | 1
User Story #10 | Select Service Center | 3 | Himmat Singh
Task_1 | Customer should be able to select the service center he want |  | Himmat Singh |  | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0
Task_2 | He should be able to select the time slot and date details of the service |  | Himmat Singh |  | 3 | 0.5 | 2 | 0 | 3 | 0
User Story #22 | Log off |  | Aman Akash
Task_1 | 1-Option to log off from the system. |  | Aman Akash |  | 0.5 | 3 | 1 | 0.5 | 1 | 0
TOTAL |  |  |  |  | 123 | 110 | 122.5 | 128 | 85.5 | 35

## Sprint -2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #11 | Book Service | 5 | Himmat Singh
Task_1 | On selecting the Service center, Customer should be able to book for service |  | Himmat Singh |  | 8 | 5 | 3 | 1 | 2 | 0
Task_2 | Book service page should have details like own drop/car to be picked up from house |  | Himmat Singh |  | 3 | 8 | 0 | 1 | 1 | 1
Task_3 | If car to be picked up from house, get the address details |  | Himmat Singh |  | 3 | 2 | 1 | 3 | 2 | 1
User Story #12 | Approve or Reject Service | 3 | Himmat Singh
Task_1 | Vendor should be able to see a service booked by the Customer |  | Himmat Singh |  | 0.5 | 0.5 | 3 | 2 | 3 | 1
Task_2 | Vendor should be approve/reject a service booked |  | Himmat Singh |  | 5 | 5 | 3 | 1 | 2 | 0
Task_3 | Approval/Rejection status should be notified to the Customer |  | Himmat Singh |  | 2 | 2 | 3 | 2 | 2 | 0
User Story #13 | Reallocate Service Center | 3 | Phani Mahesh Jonnalagadda
Task_1 | Vendor should be able to reallocate the service center different from the one Customer selected |  | Phani Mahesh Jonnalagadda |  | 8 | 3 | 5 | 1 | 0 | 1
Task_2 | That particular vendor should be able approve/reject/reallocate the request |  | Phani Mahesh Jonnalagadda |  | 2 | 2 | 3 | 1 | 1 | 1
Task_3 | On reallocation Customer should be notified about the reallocation |  | Phani Mahesh Jonnalagadda |  | 2 | 3 | 2 | 0.5 | 3 | 0
Task_4 | Vendor should provide the reallocation reason from the drop down, from the already loaded option |  | Phani Mahesh Jonnalagadda |  | 3 | 1 | 0 | 5 | 3 | 0
User Story #14 | Approve/Reject reallocation | 3 | Vishal Choudary
Task_1 | Customer should be able to approve/Reject the reallocation |  | Vishal Choudary |  | 6 | 2 | 8 | 8 | 3 | 5
Task_2 | On approval, vendor should be notified |  | Vishal Choudary |  | 1 | 0.5 | 0.5 | 1 | 1 | 0
User Story #15 | Cancel Service | 3 | Aman Akash
Task_1 | Customer should be able to cancel a booked service. |  | Aman Akash |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Cancellation should be done before 1 hour of the time slot selected |  | Aman Akash |  | 5 | 1 | 2 | 3 | 5 | 1
Task_3 | No cancellation should be allowed with in 1 hour of the time slot selected for booking |  | Aman Akash |  | 5 | 3 | 5 | 3 | 3 | 1
User Story#16 | Service- Customer review | 1 | Aman Akash
Task_1 | Notification should be sent to Customer on closing the service to update the review for the service provided. |  | Aman Akash |  | 5 | 2 | 1 | 3 | 1 | 0
Task_2 | Notification can be displayed in the notification page |  | Aman Akash |  | 3 | 2 | 3 | 1 | 2 | 1
Task_3 | Feedback can be in questionaire form, with rating 1-5 |  | Aman Akash |  | 1 | 0.5 | 0 | 1 | 1 | 9
User Story#17 | Bill Generation | 3 | Vishal Choudary
Task_1 | Customer should be directed to payment gateway and the corresponding bill details will be stored in database while handovering the car to the Customer. |  | Vishal Choudary |  | 3 | 1 | 5 | 3 | 0 | 1
User Story#18 | Payment | 5 | Phani Mahesh Jonnalagadda
Task_1 | The Customer will pay the corresponding bill amount through the gateaway and he/she will have different options to pay the amount like credit card,debit card,upi. |  | Phani Mahesh Jonnalagadda |  | 5 | 3 | 5 | 3 | 1 | 1
Task_2 | Upon selection of the mode of payment different fileds will come for different options and Customer will fill those fileds |  | Phani Mahesh Jonnalagadda |  | 1 | 3 | 3 | 2 | 1 | 5
Task_3 | After successful payment the Customer will be displayed a success message that ‘Payment is successfull’ and the status of the bill should be changed from ‘pending’ to ‘paid’ in the datatbase. |  | Phani Mahesh Jonnalagadda |  | 0.5 | 0.5 | 3 | 5 | 2 | 1
Task_4 | Provide an option for the Customer to Print the bill. |  | Phani Mahesh Jonnalagadda |  | 3 | 3 | 0.5 | 2 | 1 | 0
User Story#19 | Feedback Report | 1 | Aman Akash
Task_1 | Admin should be able to generate the feedback report in an excel sheet |  | Aman Akash |  | 6 | 3 | 8 | 9 | 3 | 0
User Story#20 | Admin Report | 1 | Phani Mahesh Jonnalagadda
Task_1 | Admin should be able to generate the service report in an excel sheet. |  | Phani Mahesh Jonnalagadda |  | 3 | 1 | 5 | 3 | 5 | 1
Task_2 | It should have the details of services availed, most used services, Customers who availed more services etc |  | Phani Mahesh Jonnalagadda |  | 5 | 2 | 2 | 5 | 2 | 1
User Story#21 | Discounts | 1 | Vishal Choudary
Task_1 | from the report result, the top most Customers should be provided with 20% discounts on their next availed service |  | Vishal Choudary |  | 5 | 1 | 3 | 0 | 1 | 8
Task_2 | the least used service center should be provided 20% discounts, for all Customers |  | Vishal Choudary |  | 3 | 1 | 5 | 1 | 0 | 1
Task_3 | This can be handled with couponcode etc |  | Vishal Choudary |  | 2 | 2 | 5 | 3 | 0 | 2
TOTAL |  |  |  |  | 106 | 68 | 90 | 73.5 | 51 | 43

## Sprint - 3
Sprint Backlog Car Servicing Project ID: A027 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
User Story #4
Task_1
Task_2
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A