## Cover Page
Car Servicing
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Initial Selection | Customer/Admin/Vendor | As Vendor/Customer/Admin I want the system to allow to Customer to choose Vendor/Customer/Admin Login/Registration | 1-Screen should display the option for Admin/Vendor login / Registration and Customer login / Registration | Critical | 1 | 5 | Yes | 1 | 1 | 5
US_2 | User Registration | User -Customer/vendor | As User I want the system to procure the fundamental details of the User | 1-When the User clicks on Admin Registration link, it should re-direct to registration form 2-Admin needs to fill some of the basic attributes/fields as mentioned below in the requirement: First Name, Last Name, Contact Number, Email, Password Name should be in range 4-50 Contact number should be of 10 digits Password should be of minimum 6 letters with special characters included. Note - Trainees can add/neglect fields that will be appropriate and validations should be handled for all fields User should have option to select their Role - Customer/Vendor - Use radio button If vendor role is selected - Vendor Id should be displayed - which is an auto generated field. 3-Before entering the next field, each field should be validated and appropriate error message should be displayed near the corresponding text box. 4-User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 4-Post-successful field level validation, save the information in the database 5-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7-Admin should be able to view the New vendor registration 8-Admin should approve / reject the vendor Request. 9-If rejected, the Vendor should not be allowed to login with the registered credentials 10-Vendor should be notified upon approval/rejection while trying to enter the application. | Critical | 1 | 8 | Yes | 1 | 1 | 8
US_3 | User Authentication | User | As User I want the system to authenticate the User credentials of the registered admin | 1-A registered User – is able click ‘Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical | 1 | 5 | Yes | 1 | 1 | 3
US_4 | Admin Registration | Admin | As Admin I want the system to procure the fundamental details of the Admin | 1-Admin should select the Admin option. 2-Admin's User id and password should be pre-loaded in the database, which can be used to log in. | Critical | 1 | 5 | Yes | 1 | 1 | 5
US_5 | Admin Authentication | Admin | As Admin I want the system to authenticate the user credentials of the registered Admin | 1-A registered Admin – is able click ‘Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical | 1 | 5 | Yes | 1 | 1 | 3
US_6 | Admin Approval | Admin | As Admin I want to approve the vendor registered | 1-Any vendor registration should be approved by Admin 2- Only on approval, vendor should be able to login 3- Error message such as approval pending should be displayed, when such vendor tries to login | Critical | 1 | 5 | Yes | 1 | 1 | 5
US_7 | Vendor details | Vendor | As Vendor I want the system to procure the Vendor contact details | 1-Vendor should be able to fill in his details like address/ phone number, email and other contact information. 2-Vendor should be able to update his existing details 3- Fields like vendor id should not be editable | Critical | 1 | 5 | Yes | 1 | 1 | 3
US_8 | Service Center details | Vendor | As Vendor I want the system to procure the Service details | 1- Vendor should click on the add service tab to select the service he provides. 2-All category divisions available should be listed for the Service and Vendor should be able to select one 3-Vendor providing service should provide the contact details, available time and Maps option to locate 4-Vendor should have a field to update his service details Clicking ‘Submit’ should validate the datatype constraints for each field 5-Vendor failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7-The service details entered should be linked with the vendor ID creating it 8-Vendor should have the option to edit / delete the Service details entered by them. | Critical | 2 | 8 | Yes | 2 | 2 | 8
US_9 | Search Service center | Admin/Customer/Vendor | As Customers I want to search option | 1- All Users should be able to search for service center 2-Search can be based on the service type, location,name of the service center. 3- Search result should display the service center details 4- clicking the service center displayed, it should open the service center details page 5- From which Customer should be able book for service 6-Vendor should be edit/delete the details Note - Use Pagenation wherever applicable -for listing - like search result | Medium | 2 | 5 | Yes | 2 | 2 | 5
US_10 | Select Service center | Customer | As Customer I want to select the service center | 1-Customer should be able to select the service center he want 2- He should be able to select the time slot and date details of the service | Critical | 2 | 3 | Yes | 2 | 2 | 3
US_11 | Book service | Customer | As Customer I want to Book a service | 1-On selecting the Service center, Customer should be able to book for service 2- Book service page should have details like own drop/car to be picked up from house 3-If car to be picked up from house, get the address details | Critical | 2 | 5 | Yes | 2 | 2 | 5
US_12 | Approve/Reject Service | Vendor | As Vendor I want to approve/reject a booked service | 1-Vendor should be able to see a service booked by the Customer 2-Vendor should be approve/reject a service booked 3-Approval/Rejection status should be notified to the Customer | Critical | 2 | 3 | Yes | 2 | 2 | 3
US_13 | Reallocate service center | Vendor | As Vendor, I want to reallocate the service center from the one Customer requested | 1-Vendor should be able to reallocate the service center different from the one Customer selected 2-That particular vendor should be able approve/reject/reallocate the request 3-On reallocation Customer should be notified about the reallocation 4-Vendor should provide the reallocation reason from the drop down, from the already loaded option | Medium | 2 | 3 | Yes | 2 | 2 | 3
US_14 | Approve/Reject reallocation | Customer | As Customer I want to approve the reallocation | 1-Customer should be able to approve/Reject the reallocation 2- On approval, vendor should be notified | Medium | 2 | 3 | Yes | 2 | 2 | 3
US_15 | Cancel Service | Customer | As Customer I want to cancel the booked service | 1-Customer should be able to cancel a booked service. 2- Cancellation should be done before 1 hour of the time slot selected 3- No cancellation should be allowed with in 1 hour of the time slot selected for booking | Medium | 2 | 3 | Yes | 2 | 2 | 3
US_16 | Service- Customer review | Customer | As Customer I want the system to allow the Customer to write review | 1-Notification should be sent to Customer on closing the service to update the review for the service provided. 2-Notification can be displayed in the notification page 3- Feedback can be in questionaire form, with rating 1-5 | Low | 2 | 1 | No | 2 | 2 | 1
US_17 | Bill Generation | Customer | As Customer I want the system to generate bill | 1- Customer should be directed to payment gateway and the corresponding bill details will be stored in database while handovering the car to the Customer. | Critical | 2 | 3 | Yes | 2 | 2 | 3
US_18 | Payment | Customer | As Customer I want the system to allow Customer to pay for the availed service | 1-The Customer will pay the corresponding bill amount through the gateaway and he/she will have different options to pay the amount like Credit card,debit card,upi. 2-Upon selection of the mode of payment different fileds will come for different options and Customer will fill those fileds 3-After successful payment the Customer will be displayed a success message that ‘Payment is successfull’ and the status of the bill should be changed from ‘pending’ to ‘paid’ in the datatbase. 4-Provide an option for the Customer to Print the bill. Note -Payment has to be mocked by having an an amount account and when paid, the amount must be reduced. | Critical | 2 | 5 | Yes | 2 | 2 | 5
US_19 | Feedback Report | Admin | As Admin I want to generate Feedback report | 1-Admin should be able to generate the feedback report in an excel sheet | Low | 2 | 1 | No | 2 | 2 | 1
US_20 | Admin Report | Admin | As Admin I want to generate Service report | 1-Admin should be able to generate the service report in an excel sheet. 2-It should have the details of services availed, most used services, Customers who availed more services etc | Low | 2 | 1 | No | 2 | 2 | 1
US_21 | Discounts | Admin | As Admin I want to give discounts for the Customers | 1-from the report result, the top most Customers should be provided with 20% discounts on their next availed service 2-the least used service center should be provided 20% discounts, for all Customers 3- This can be handled with couponcode etc | Low | 2 | 1 | No | 2 | 2 | 1
US_22 | Log off | Vendor/Customer/Admin | As Vendor/Customer/Admin I want the system to enable Customer to logoff | 1-Option to log off from the system. | Low | 1 | 1 | Yes | 1 | 1 | 1

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000